## Slide 1: 5th PIRC Meeting (Mt. Abu, 30th May 2019)
Progress Review Presentations

## Slide 2
Sr. No. | State | State Representatives |  | CWC Representatives | 
 |  | Name | Designation | Name | Designation
1. | Andhra Pradesh | Sh.L.V.Ramana Murty | SE | Sh. D. Ganesh Kumar | Dy. Director, M&A (KGBO Hyderabad)
2. | Assam | Sh. Sayed Nur Rahman | CHD (Irrigation), BTC | Sh P.M.Scott | CE (B&BBO, Shillong)
3. | Bihar | Sh. Ram Pukar Ranjan | EIC, CAD | Sh.Shashi Rakesh | SE (LGBO Patna )
4. | Chhattisgarh | Sh. A. K. Somawar | CE | Sh.Aditya Sharma | CE (NBO Bhopal)
5. | Goa | Sh. S.T. Nadkarni | CE | Sh.Sushil Kumar | CE (MSO Bengaluru)
6 | Gujarat | Sh. T.S. Shah | CE | Sh.M.P.Singh | CE (MTBO Gandhinagar)
7. | J&K | Sh. Mohd. Harun Malik | Director, KAS | Sh. Yoki Vijay IBO Chandigarh | Director M&A
8. | Jharkhand | Sh. Gopaljee | SE | Sh.Shashi Rakesh | SE(LGBO Patna)
INDEX
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Consolidated

## Slide 3
Sr. No. | State | State Representatives |  | CWC Representatives | 
 |  | Name | Designation | Name | Designation
9. | Karnataka | Sh. B.R.Anil Kumar | CE | Sh.Sushil Kumar | CE (MSO Bengaluru)
10. | Kerala | Sh. B. Shaji | SE | Sh.Krishnanunni.N.M | CE (C & SRO, CWC, Coimbatore)
11. | Madhya Pradesh | Sh. Shrikant Dandekar | Commissioner (CAD) | Sh.Aditya Sharma | CE (NBO Bhopal)
12. | Maharashtra | Sh.Rajendra Pawar | Secretary(CAD) | Sh.D.K.Tiwari | CE (MCO Nagpur)
13. | Manipur | Sh. Suresh Singh Ningombam | Addl CE | Sh P.M.Scott | CE (B&BBO, Shillong)
14. | Odisha | Sh. Jena | Principal Secretary Of DOWR | Sh.Ambarish Nayak | CE (MERO Bhubaneswar)
INDEX (contd.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Consolidated

## Slide 4
Sr. No. | State | State Representatives |  | CWC Representatives | 
 |  | Name | Designation | Name | Designation
15. | Rajasthan | Sh Naveen Mahajan | Secretary, WR, | Sh. Vivek Kumar Singh | DD (YBO, Delhi)
16. | Telangana | Sh. Anantha Ramulu | SE | Sh. D. Ganesh Kumar | DD (KGBO Hyderabad)
17. | Uttar Pradesh | Devendra Pratap Shukla | BSA | Sh.Bhopal Singh | CE (UGBO Lucknow)
INDEX (contd.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Consolidated

## Slide 5
Status of Inclusion
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Out of 99 projects, 9 projects are not being proposed by State Governments for inclusion under CADWM program for CAD works. One Project of Rajasthan (Narmada Canal) is included for Non- Structural intervention only. These projects are:
Sl. No. | State | Project | CCA as per Cabinet Note ( Th. ha) | Remarks
1 | Maharashtra | Dongargaon | 2.76 | CAD Works completed through state funds
2 | Maharashtra | Wang | 7.06 | CAD Works not required; direct lifting by farmers
3 | Maharashtra | Nardave | 12.28 | CAD Works not required; direct lifting by farmers
4 | Maharashtra | Warna | 54.74 | CAD Works not required; direct lifting by farmers
5 | Punjab | Kandi Canal Stage II | 23.33 | Works completed under AIBP
6 | Punjab | Ist Patiala feeder & Kotla Branch | 9.1 | Proposed under ISBIG for enhanced target
7 | Andhra Pradesh | Maddigedda | 1.42 | Works completed through state funds
8 | Jammu & Kashmir | Modernisation of Ravi Canal | 50.75 | Works completed earlier through Central funding
9 | Uttar Pradesh | Bansagar | 150.13 | Works completed through state funds
10 | Rajasthan | Narmada Canal project* | 245.88 | Structural Works completed under AIBP
 |  | Total | 557.45 | 

## Slide 6
Status of Inclusion (contd.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
As of now, 87* projects in balance Culturable Command Area (CCA) of 43.51 lakh hectares have been included under CADWM programme with Central Assistance (CA) of Rs 7,927 Crore against estimated cost of Rs 17,876 Crore.
Chart: 
| Projects Included in 2016-17 | Projects Included in 2017-18 | Projects Included in 2018-19 | Balance Projects to be included | Deemed Completed Projects | Originally Included Projects
 | 18 | 29 | 2 | 4 | 9 | 37
Sl. No. | Projects yet to be included
1 | Punpun (Bihar)
2 | Karipuzha (Kerala)
3 | Madhya Ganga (Uttar Pradesh)
* Includes Narmada Canal Project of Rajasthan for non-structural intervention.

## Slide 7
Consolidated Status
Number of Projects : 90(99-9) Projects Included: 87 Projects Availing CA: 70 Projects Reporting Progress:53
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 17875.98 | 7927.77 | 4350.78 | 13734
Progress | 4828.41 | 2380.2 | 1343.82 | 6981
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Consolidated

## Slide 8
CCA Progress
Sr. No. | State | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1. | AP | 178.62 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 61.60
2. | Assam | 46.62 | 0.00 | 1.19 | 13.06 | 14.25 | 30.57 | 32.40
3. | Bihar | 32.24 | 2.25 | 5.49 | 4.00 | 11.74 | 36.40 | 18.80
4. | Chhattisgarh | 42.63 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 11.00
5. | Goa | 8.67 | 0.01 | 0.01 | 0.75 | 0.77 | 8.83 | 3.95
6 | Gujarat | 1363.86 | 385.33 | 290.06 | 260.17 | 935.56 | 68.60 | 187.87
7. | J&K | 2.46 | 0.00 | 0.00 | 1.28 | 1.28 | 52.11 | 1.18
8. | Jharkhand | 66.65 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 13.33
9. | Karnataka | 84.03 | 11.08 | 11.50 | 8.35 | 30.93 | 36.81 | 11.17
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
( Area in Th. Ha.)

## Slide 9
CCA Progress(contd.)
Sr. No. | State | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
10. | Kerala | 17.25 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 2.40
11. | Madhya Pradesh | 635.13 | 76.33 | 83.23 | 46.88 | 210.04 | 33.07 | 118.50
12. | Maharashtra | 517.40 | 5.27 | 18.42 | 34.19 | 57.88 | 11.19 | 80.50
13. | Manipur | 22.04 | 0.00 | 5.03 | 0.00 | 5.03 | 23.00 | 17.01
14. | Odisha | 236.30 | 9.49 | 26.99 | 18.69 | 55.17 | 23.35 | 35.21
15. | Rajasthan | 43.49 | 6.86 | 7.22 | 7.08 | 21.17 | 48.67 | 9.50
16. | Telangana | 529.03 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 141.78
17. | Uttar Pradesh | 524.38 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 172.75
 | Total | 4350.78 | 496.62 | 449.14 | 394.44 | 1343.82 | 30.89 | 918.94
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
( Area in Th. Ha.)

## Slide 10
WUA Progress
Sr. No. | State | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1. | AP | 418 | 5 | 0 | 0 | 0 | 5 | 1 | 292
2. | Assam | 100 | 3 | 20 | 5 | 44 | 72 | 72 | 28
3. | Bihar | 30 | 0 | 0 | 0 | 8 | 8 | 27 | 22
4. | Chhattisgarh | 32 | 10 | 10 | 0 | 0 | 20 | 63 | Not Reported
5. | Goa | 150 | 42 | 0 | 0 | 0 | 42 | 28 | 33
6. | Gujarat | 4466 | 1894 | 428 | 46 | 526 | 2894 | 65 | 1200
7. | J&K | 6 | 0 | 0 | 0 | 2 | 2 | 33 | 3
8. | Jharkhand | 256 | 0 | 0 | 0 |  | 0 | 0 | 106
9. | Karnataka | 807 | 0 | 46 | 98 | 91 | 235 | 29 | 534
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 11
WUA Progress (Contd.)
Sr. No. | State | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
10. | Kerala | 240 | 95 | 0 | 0 | 19 | 114 | 48 | 32
11. | Madhya Pradesh | 437 | 286 | 40 | 15 | 0 | 351 | 80 | 31
12. | Maharashtra | 1689 | 0 | 648 | 0 | 193 | 841 | 50 | 408
13. | Manipur | 74 | 0 | 0 | 29 | 5 | 34 | 46 | 40
14. | Odisha | 545 | 0 | 16 | 69 | 27 | 112 | 21 | 124
15. | Rajasthan | 2268 | 2180 | 56 | 1 | 14 | 2251 | 99 | 17
16. | Telangana | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 8
17. | Uttar Pradesh | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Total | 13734 | 4515 | 1264 | 263 | 929 | 6981 | 51 | 2878
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 12
CA Release Progress
Sr. No. | State | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1. | AP | 349.40 | 0.00 | 0.00 | 69.18 | 69.18 | 19.80 | 118.70
2. | Assam | 106.28 | 0.00 | 0.00 | 3.56 | 3.56 | 3.35 | 83.23
3. | Bihar | 55.60 | 12.60 | 8.76 | 14.42 | 35.82 | 64.46 | 7.53
4. | Chhattisgarh | 79.57 | 0.00 | 11.80 | 9.93 | 21.70 | 27.28 | 19.90
5. | Goa | 18.70 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 7.15
6 | Gujarat | 2510.88 | 681.64 | 690.48 | 347.04 | 1719.16 | 68.47 | 499.75
7. | J&K | 5.24 | 0.00 | 0.00 | 1.70 | 1.70 | 32.44 | 1.40
8. | Jharkhand | 133.32 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 149.50
9. | Karnataka | 179.90 | 31.42 | 15.25 | 13.49 | 60.16 | 33.44 | 23.30
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 13
CA Release Progress( Contd.)
Sr. No. | State | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
10. | Kerala | 48.71 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 4.00
11. | Madhya Pradesh | 1242.48 | 77.74 | 102.80 | 70.91 | 251.40 | 20.24 | Not Reported
12. | Maharashtra | 983.39 | 15.17 | 32.81 | 25.79 | 73.77 | 196.90 | 101.00
13. | Manipur | 63.66 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 46.08
14. | Odisha | 420.20 | 35.28 | 58.57 | 3.65 | 97.49 | 23.20 | 107.34
15. | Rajisthan | 115.30 | 0.00 | 2.48 | 7.44 | 9.92 | 8.60 | 31.20
16. | Telangana | 700.22 | 0.00 | 10.22 | 26.12 | 36.34 | 5.19 | 103.93
17. | Uttar Pradesh | 914.92 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 300.31
 | Total | 7927.77 | 853.85 | 933.17 | 593.23 | 2380.20 | 30.02 | 1604.31
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 14
Total Expenditure Progress
Sr. No. | State | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1. | AP | 971.42 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 411.95
2. | Assam | 215.46 | 0.00 | 8.76 | 13.21 | 21.97 | 10.20 | 165.16
3. | Bihar | 148.57 | 7.86 | 20.20 | 17.60 | 45.58 | 30.68 | 89.41
4. | Chhattisgarh | 159.76 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 68.00
5. | Goa | 153.67 | 4.72 | 7.17 | 9.09 | 21.00 | 13.65 | 70.00
6 | Gujarat | 5021.77 | 1435.91 | 1224.73 | 861.68 | 3522.32 | 70.14 | 999.49
7. | J&K | 11.64 | 0.00 | 0.00 | 1.74 | 1.74 | 14.95 | 9.90
8. | Jharkhand | 747.53 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 149.50
9. | Karnataka | 1012.17 | 38.94 | 41.64 | 32.44 | 113.00 | 11.17 | 64.32
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 15
Total Expenditure Progress ( Contd.)
Sr. No. | State | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
10. | Kerala | 107.29 | 1.54 | 0.00 | 0.00 | 1.54 | 1.44 | 8.00
11. | Madhya Pradesh | 2345.39 | 189.69 | 308.25 | 120.41 | 618.35 | 26.36 | 131.20
12. | Maharashtra | 2066.00 | 1.32 | 41.30 | 113.80 | 156.40 | 7.57 | 213.05
13. | Manipur | 122.71 | 0.00 | 19.34 | 0.00 | 19.34 | 16.00 | 103.37
14. | Odisha | 1265.20 | 58.76 | 100.80 | 109.40 | 268.90 | 21.25 | 213.85
15. | Rajasthan | 220.49 | 10.43 | 13.00 | 14.90 | 38.27 | 17.36 | 58.50
16. | Telangana | 1478.81 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 648.02
17. | Uttar Pradesh | 1828.10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 600.00
 | Total | 17875.98 | 1749.17 | 1785.19 | 1294.27 | 4828.41 | 27.01 | 4003.73
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 16
Broad Review
Sr. No. | State | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | AP | 266.1 | 87.49 | 0 | 87.49 | 32.88 | 294.9 | 230.3 | 78.09
2. | Assam | 54.12 | 7.5 | 14.25 | 21.75 | 40.19 | 114.33 | 81.78 | 71.53
3. | Bihar | 32.47 | 1.96 | 11.74 | 13.7 | 42.19 | 39.61 | 26.5 | 66.90
4. | Chhattisgarh | 42.63 | 0 | 0 | 0 | 0 | 44.63 | 38.8 | 86.94
5. | Goa | 14.52 | 5.85 | 0.77 | 6.62 | 45.59 | 21.05 | 11.83 | 56.20
6 | Gujarat | 1792 | 602.45 | 935.56 | 1538 | 85.83 | 1792 | 1647.2 | 91.92
7. | J&K | 5.5 | 3.04 | 1.28 | 4.32 | 78.55 | 10.69 | 8.12 | 75.96
8. | Jharkhand | 66.65 | 0 | 0 | 0 | 0 | 236.85 | 107.33 | 45.32
9. | Karnataka | 176.48 | 90.93 | 30.93 | 121.86 | 69.05 | 252.81 | 241.22 | 95.42
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 17
Broad Review ( Contd.)
Sr. No. | State | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
10. | Kerala | 19.24 | 1.99 | 0 | 1.99 | 10.34 | 30.72 | 27.82 | 90.56
11. | Madhya Pradesh | 664.44 | 101.78 | 210.04 | 311.82 | 46.93 | 847.77 | 775.85 | 91.52
12. | Maharashtra | 706 | 205.4 | 57.88 | 263.28 | 37.29 | 777.5 | 74.01 | 9.52
13. | Manipur | 22.04 | 8.97 | 5.03 | 14 | 63.52 | 36.99 | 20.96 | 56.66
14. | Odisha | 238.96 | 2.75 | 55.17 | 57.92 | 24.24 | 331.56 | 177.61 | 53.57
15. | Rajisthan | 291.69 | 247.39 | 21.17 | 268.56 | 92.07 | 342.39 | 342.32 | 99.98
16. | Telangana | 529.03 | 0 | 0 | 0 | 0 | 636.04 | 324.12 | 50.96
17. | Uttar Pradesh | 524.38 | 0 | 0 | 0 | 0 | 663.9 | 221.15 | 33.31
 | Total | 5446.25 | 1367.50 | 1343.82 | 2711.32 | 49.78 | 6473.74 | 4356.87 | 67.30
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 18
CADWM- Monitoring
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Officers of CAD Wing, MoWR, RD & GR has undertaken visits to 16 projects while CWC CAD cells and Project Monitoring Unit (PMU) has undertaken 123 & 142 monitoring visits respectively to CAD projects during 2018-19.
Four meetings of the Project Implementation Review Committee (PIRC) have been held so far. The 4th meeting was held on 4-5th February 2019 at Nagpur.
Onsite MIS training was also conducted on 8 places : CSMRS , New Delhi (25/09/2018); Nasik (22/05/2018); Vadodara (10/05/2018); Lucknow(03/07/2018); Bhubaneswar (26/07/2018); Jaipur(25/09/2018), Nagpur(04/10/2018); Bikaner(14/01/2019).
CA release proposals were processed thorugh online system in 41 cases.
61 observations of field inspection were recorded online in respect of 33 projects.
Progress was captured on MIS by State nodals outlet-wise.

## Slide 19
LAG in Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Chart: CCA in lakh ha.
| Under Progress | Completed | Non Starter
 | 22.12 | 12.42 | 8.38

## Slide 20
STATE/ PROJECTS LAGGING IN PROGRESS
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
17 Projects (in 10 states) out of 87 included Projects covering 8.38 Lakh Ha of CCA ( about 20 % of total target) with CA share of Rs 1628 Crore have yet not availed any CA.
Non-Starter State / Projects ( i.e. ‘Nil’ CA availed)
Assam(2/3 Projects; Dhansiri, Boralia)
Goa (1/1 Project; Tillari)
Jharkhand (1/1 Projects; Subarnrekha)
Karnataka (1/5 Projects; NLBC)
Kerala (1/1 Project; Muvattapuzha)
Maharashtra (4/22 Projects; Nandur Madhmaheswar, Aruna, Lower Pedhi & Kudali)
Manipur (2/2 Projects; Thoubal, Dolaithabi)
Rajasthan (1/2 projects; Narmada Canal)
Telangana (2/11 Projects; Peddavagu, Rajiv Bhima L.I.)
Uttar Pradesh (2/2 Projects; Arjun Sahayak, Saryu Nahar)

## Slide 21
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
√ | Capacity related issues of Contractors/Suppliers.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 22
Thank You

## Slide 23
Andhra Pradesh
Number of Projects : 7 Projects Included: 7 Projects Availing CA: 7 Projects Reporting Progress:0
Physical Progress
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 970.982 | 349.3734 | 178.62 | 422
Progress | 0 | 69.18 | 0 | 0
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 24
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Gundalkamma | 32.400 | 0 | 0 | 0 | 0 | 0 | 23.328
2. | Musurumilli | 5.915 | 0 | 0 | 0 | 0 | 0 | 1.137
3. | Pushkara LIS | 46.546 | 0 | 0 | 0 | 0 | 0 | 11.476
4. | Tadipudi LIS | 54.346 | 0 | 0 | 0 | 0 | 0 | 13.168
5. | Taraka Thirtha Sagaram Reservoir | 4.351 | 0 | 0 | 0 | 0 | 0 | 0.820
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 29.138 | 0 | 0 | 0 | 0 | 0 | 8.499
7. | Yerracalva | 5.924 | 0 | 0 | 0 | 0 | 0 | 3.172
 | TOTAL | 178.620 | 0 | 0 | 0 | 0 | 0 | 61.600
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 25
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Gundalkamma | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40
2. | Musurumilli | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11
3. | Pushkara LIS | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100
4. | Tadipudi LIS | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 90
5. | Taraka Thirtha Sagaram Reservoir | 20 | 0 | 0 | 0 | 0 | 0 | 0 | .....
6. | Sardar Gouthu Lachanna Thotapali Barrage Project | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 45
7. | Yerracalva | 11 | 5 | 0 | 0 | 0 | 5 | 45.45 | 6
 | TOTAL | 418 | 5 | 0 | 0 | 0 | 5 | 1.196 | 292
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 26
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Gundalkamma | 47.1481 | 0 | 0 | 3.64 | 3.64 | 7.72 | 8.51
2. | Musurumilli | 12.6772 | 0 | 0 | 4.49 | 4.49 | 35.41 | 6.33
3. | Pushkara LIS | 99.6564 | 0 | 0 | 35.85 | 35.85 | 35.97 | 33.24
4. | Tadipudi LIS | 109.3363 | 0 | 0 | 16.40 | 16.40 | 15 | 32.80
5. | Taraka Thirtha Sagaram Reservoir | 10.1452 | 0 | 0 | 0.61 | 0.61 | 6.01 | 6.00
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 58.5332 | 0 | 0 | 6.37 | 6.37 | 10.88 | 27.49
7. | Yerracalva | 11.8752 | 0 | 0 | 1.82 | 1.82 | 15.33 | 4.33
 | TOTAL | 349.4 | 0 | 0 | 69.18 | 69.18 | 19.80 | 118.7
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 27
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Gundalkamma | 102.79 | 0 | 0 | 0 | 0 | 0 | 90.64
2. | Musurumilli | 31.73 | 0 | 0 | 0 | 0 | 0 | 13.17
3. | Pushkara LIS | 240.87 | 0 | 0 | 0 | 0 | 0 | 96.35
4. | Tadipudi LIS | 277.73 | 0 | 0 | 0 | 0 | 0 | 124.98
5. | Taraka Thirtha Sagaram Reservoir | 25.92 | 0 | 0 | 0 | 0 | 0 | 6.66
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 265.84 | 0 | 0 | 0 | 0 | 0 | 59.76
7. | Yerracalva | 26.54 | 0 | 0 | 0 | 0 | 0 | 20.39
 | TOTAL | 971.42 | 0 | 0 | 0 | 0 | 0 | 411.95
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 28
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Gundalkamma | 32.4 | 0 | 0 | 0 | 0 | 32.4 | 28.42 | 87.72
2. | Musurumilli | 9.16 | 3.25 | 0 | 3.25 | 35.48 | 9.16 | 9.16 | 100.00
3. | Pushkara LIS | 75.24 | 28.69 | 0 | 28.69 | 38.13 | 75.24 | 59.96 | 79.69
4. | Tadipudi LIS | 83.61 | 29.26 | 0 | 29.26 | 35 | 83.61 | 63.76 | 76.26
5. | Taraka Thirtha Sagaram Reservoir | 10 | 5.65 | 0 | 5.65 | 56.5 | 10 | 0 | 0
6 | Sardar Gouthu Lachanna Thotapali Barrage Project | 45.7 | 16.57 | 0 | 16.57 | 36.26 | 74.46 | 62.14 | 83.45
7. | Yerracalva | 9.99 | 4.07 | 0 | 4.07 | 40.74 | 9.99 | 6.88 | 68.87
 | TOTAL | 266.1 | 87.49 | 0 | 87.49 | 32.88 | 294.9 | 230.3 | 78.11
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 30
Yerracalva project

## Slide 31
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
√ | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 32
Extra Information
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
STATUS OF CADWM WORKS
The administrative approval accorded for all 7 projects by Government of Andhra Pradesh for Survey, Planning, and Design of OFD works and for Preparation of DPR.
Technical Sanction accorded for Yerrakalva, Musurumilli and Gundlakamma Projects.
The Work of Yerrakalva Project is in progress.
Tenders are held up for Model code of conduct.
Tenders will be invited very soon.

## Slide 33
Thank You

## Slide 34
ASSAM
Number of Projects : 3 Projects Included: 3 Projects Availing CA: 1 Projects Reporting Progress:2
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 215.46 | 106.28 | 46.62 | 100
Progress | 21.97 | 3.56 | 14.25 | 72
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
ASSAM

## Slide 35
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Champamati | 6.59 | 0 | 1.191(FC) | 1.817(FC) 1.347(MI) | 4.36 | 66.12 | 2.23
2. | Dhansiri Irrigation Project | 31.12 | 0 | 0 | .140(MI), 9.758 (OFD) | 9.90 | 31.81 | 21.2
3. | Borolia | 8.9 | 0 | 0 | 0 | 0.00 | 0 | 8.92
 | TOTAL | 46.62 | 0 | 1.19 | 13.06 | 14.25 | 30.57 | 32.4
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 36
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Champamati | 40 | 0 | 20 | 5 | 0 | 25 | 62.5 | 15
2. | Dhansiri Irrigation Project | 50 | 0 | 0 | 0 | 44 | 44 | 88 | 6
3. | Borolia | 10 | 3 | 0 | 0 | 0 | 3 | 30 | 7
 | TOTAL | 100 | 3 | 20 | 5 | 44 | 72 | 72 | 28
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 37
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1. | Champamati | 13.72 | 0 | 0 | 3.56 | 3.56 | 25.95 | 6.95
2. | Dhansiri Irrigation Project | 76.04 | 0 | 0 | 0 | 0 | 0 | 66.31
3. | Borolia | 16.52 | 0 | 0 | 0 | 0 | 0 | 9.97
 | TOTAL | 106.28 | 0 | 0 | 3.56 | 3.56 | 3.35 | 83.23
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 38
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Champamati | 27.23 | 0.00 | 6.43 | 7.11 | 13.54 | 49.72 | .....
2. | Dhansiri Irrigation Project | 151.99 | 0.00 | 2.33 | 6.10 | 8.43 | 5.55 | 143.56
3. | Borolia | 36.24 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 21.60
 | TOTAL | 215.46 | 0.00 | 8.76 | 13.21 | 21.97 | 10.20 | 165.16
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 39
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Champamati | 6.59 | 0 | 4.36 | 4.36 | 66.12 | 23.54 | 23.22 | 98.64
2. | Dhansiri Irrigation Project | 38.62 | 7.50 | 9.90 | 17.40 | 45.06 | 77.23 | 55.26 | 71.55
3. | Borolia | 8.92 | 0 | 0 | 0 | 0 | 13.56 | 3.30 | 24.34
 | TOTAL | 54.12 | 7.50 | 14.25 | 21.75 | 40.19 | 114.33 | 81.78 | 71.53
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 40
Brick Lined Field Channel
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 41
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 42
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
Dhansiri Irrigation Project (Major), in Udalguri District (BTAD), Assam was initiated in the year 1975 across the river Dhansiri at Bhairabkunda near Tri-Junction of Assam, Arunachal and Bhutan.
Targeted Potential AIA = 77230 Ha.
CCA = 38615 Ha.
Intensity of Irrigation = 200%
Up to date Potential Created = 55258 Ha.
Potential Utilized = 21800 Ha.
Balance Potential to be Created = 21972 Ha.

## Slide 43
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
YEAR OF INCLUSION | 2014-15
Project Cost | Rs.151.99 Cr.
C.C.A. to be Covered | 38615 Ha.
MoU SIGNED | 22/02/2016
Revised MoU | Submitted (on 08-05-2019)
C.A. RELEASED | Rs. 9.73 Cr.
U.C. Submitted (on 08-05-2019) | Rs.8.429 Cr.
Target Date of Completion | March /2020
Up to date Physical Progress up to March/19 | 31.81%
Target up to March/2020 | 100%

## Slide 44
Thank You

## Slide 45
Bihar
Number of Projects : 2 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 148.57 | 55.6 | 32.24 | 30
Progress | 45.58 | 35.82 | 11.74 | 8
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 46
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Durgawati | 32.24 | 2.25 | 5.49 | 3.998 | 11.74 | 36.40 | 18.8
 | TOTAL | 32.24 | 2.25 | 5.49 | 4.00 | 11.74 | 36.40 | 18.8
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 47
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Durgawati | 30 | 0 | 0 | 0 | 8 | 8 | 26.67 | 22
 | TOTAL | 30 | 0 | 0 | 0 | 8 | 8 | 26.67 | 22
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 48
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Durgawati | 55.6 | 12.6 | 8.76 | 14.42 | 35.82 | 64.46 | 7.53
 | TOTAL | 55.6 | 12.6 | 8.76 | 14.42 | 35.82 | 64.46 | 7.53
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 49
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Durgawati | 148.57 | 7.86 | 20.2 | 17.6 | 45.58 | 30.68 | 89.41
 | TOTAL | 148.57 | 7.86 | 20.2 | 17.6 | 45.58 | 30.68 | 89.41
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 50
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Durgawati | 32.47 | 1.96 | 11.7 | 13.7 | 42.20 | 39.61 | 26.5 | 66.90
 | TOTAL | 32.47 | 1.96 | 11.7 | 13.7 | 42.20 | 39.61 | 26.5 | 66.90
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 51: Schematic Diagram for Durgawati Reservoir Project

## Slide 52
Photographs for Field Channels and Infrastructure for Micro Irrigation.

## Slide 54
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified). (i) The working period for construction is available only for 3-4 months due to crops in the fields. (ii) Construction work of some of the distributaries has not been started yet due to land acquisition issues.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 55
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
{ Project-specific information and Issues}
The construction of Lined field channels in about 3500 Ha. area of CCA is under progress.
Estimates of Lined field channels for 1000 Ha. is ready and is being sanctioned. Work on these will be started in June’2019.
The construction of Infrastructure development work for Micro irrigation in 200 Ha. is in Progress.
Another 1000 Ha. Area of CCA has been identified to be covered under Micro Irrigation.

## Slide 56
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
THANKS………

## Slide 57
Chhattisgarh
Number of Projects : 3 Projects Included: 3 Projects Availing CA: 3 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 159.764 | 79.57 | 42.63 | 32
Progress | 0 | 21.7 | 0 | 20
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 58
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Kelo | 22.81 | 0 | 0 | 0 | 0 | 0 | 5
2 | Kharung | 8.3 | 0 | 0 | 0 | 0 | 0 | 2.5
3 | Maniyari Tank | 11.52 | 0 | 0 | 0 | 0 | 0 | 3.5
 | TOTAL | 42.63 | 0 | 0 | 0 | 0 | 0 | 11
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 59
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Kelo | 12 | 0 | 0 | 0 | 0 | 0 | 0 | .....
2 | Kharung | 10 | 10 | 0 | 0 | 0 | 10 | 100 | 
3 | Maniyari Tank | 10 | 0 | 10 | 0 | 0 | 10 | 100 | 
 | TOTAL | 32 | 10 | 10 | 0 | 0 | 20 | 62.5 | 
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 60
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Kelo | 40.52 | 0 | 11.8 | 0 | 11.8 | 29.08 | 10
2 | Kharung | 16.43 | 0 | 0 | 4.95 | 4.95 | 30.14 | 4.95
3 | Maniyari Tank | 22.63 | 0 | 0 | 4.98 | 4.98 | 22.01 | 4.98
 | TOTAL | 79.57 | 0 | 11.8 | 9.93 | 21.7 | 27.28 | 19.9
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 61
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Kelo | 81.2089 | 0 | 0 | 0 | 0 | 0 | 40
2 | Kharung | 33.1828 | 0 | 0 | 0 | 0 | 0 | 12
3 | Maniyari Tank | 45.3722 | 0 | 0 | 0 | 0 | 0 | 16
 | TOTAL | 159.764 | 0 | 0 | 0 | 0 | 0 | 68
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 62
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Kelo | 22.81 | 0 | 0 | 0 | 0 | 22.81 | 17 | 74.40
2 | Kharung | 8.3 | 0 | 0 | 0 | 0 | 10.3 | 10.3 | 100.00
3 | Maniyari Tank | 11.515 | 0 | 0 | 0 | 0 | 11.52 | 11.5 | 100.00
 | TOTAL | 42.625 | 0 | 0 | 0 | 0 | 44.63 | 38.8 | 86.91
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 63
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
√ | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 64
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
CHHATTISGARH
Extra Slides
  Tender called for CADWM works of Kelo, Kharung and Maniyari Projects have been cancelled because of very much high rates quoted by tenderers. After expiry of Model code of Conduct for Loksabha Election, retendering process will be started.

## Slide 65
Goa
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 0 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 153.67 | 18.7 | 8.667 | 150
Progress | 21 | 0 | 0.765 | 42
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 66
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Tillari | 8.667 | 0.01 | 0.01 | 0.75 | 0.77 | 8.83 | 3.95
 | TOTAL | 8.667 | 0.01 | 0.01 | 0.75 | 0.77 | 8.83 | 3.95
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 67
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Tillari | 150 | 42 | 0 | 0 | 0 | 42 | 28 | 33
 | TOTAL | 150 | 42 | 0 | 0 | 0 | 42 | 28 | 33
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 68
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Tillari | 18.70 | 0 | 0 | 0 | 0 | 0 | 7.15
 | TOTAL | 18.70 | 0 | 0 | 0 | 0 | 0 | 7.15
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 69
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Tillari | 153.67 | 4.72 | 7.17 | 9.09 | 21 | 13.65 | 70
 | TOTAL | 153.67 | 4.72 | 7.17 | 9.09 | 21 | 13.65 | 70
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 70
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Tillari | 14.52 | 5.85 | 0.77 | 6.62 | 45.58 | 21.05 | 11.83 | 56.20
 | TOTAL | 14.52 | 5.85 | 0.77 | 6.62 | 45.58 | 21.05 | 11.83 | 56.20
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 71
Glimpses Of Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 72
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 73
Gujarat
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 1 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (in th. Ha.)
Target | 5021.765 | 2510.883 | 1363.859 | 4466
Progress | 3522.315 | 1719.155 | 935.556 | 2894
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 74
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Sardar Sarovar Project | 1363.859 | 385.330 | 290.061 | 260.165 | 935.556 | 68.60 | 187.869
 | TOTAL | 1363.859 | 385.330 | 290.061 | 260.165 | 935.556 | 68.60 | 187.869
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 75
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress (Registered) |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Sardar Sarovar Project | 4466 | 1894 | 428 | 46 | 526 | 2894 | 64.80 | 1200
 | TOTAL | 4466 | 1894 | 428 | 46 | 526 | 2894 | 64.80 | 1200
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 76
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Sardar Sarovar Project | 2510.883 | 681.644 | 690.476 | 347.040 | 1719.160 | 68.468 | 499.750
 | TOTAL | 2510.883 | 681.644 | 690.476 | 347.040 | 1719.160 | 68.468 | 499.750
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 77
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Sardar Sarovar Project | 5021.765 | 1435.906 | 1224.729 | 861.680 | 3522.315 | 70.141 | 999.490
 | TOTAL | 5021.765 | 1435.906 | 1224.729 | 861.680 | 3522.315 | 70.141 | 999.490
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 78
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed as on 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Sardar Sarovar Project | 1792 | 602.446 | 935.556 | 1538 | 85.83 | 1792 | 1647.15 | 91.92
 | TOTAL | 1792 | 602.446 | 935.556 | 1538 | 85.83 | 1792 | 1647.15 | 91.92
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 79: Progress of Canal Network
79
100%
96%
95%
88%
84%
Culturable Command Area Developed up to March-2019
15 lakh Ha.
Open Gravity Channels

## Slide 80
SUB MINOR- 07-JSM
DISTRY - JASHAVANTPURA MINOR (D.O.)
BRANCH- AMARAPURA
VILLAGE- JASHAVANTPURA, TALUKA- HARIJ
DISTRICT- PATAN
TURN OUT
AIR VALVE
Air Valve and Turnout

## Slide 81
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 82: - CCA developed upto subminor (UGPL) under Sardar Sarovar Project is 15 lakhs ha upto March-2019. - UGPL work in progress for the other areas of CCA
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides

## Slide 83
Jammu And Kashmir
Number of Projects : 3 Projects Included: 3 Projects Availing CA: 3 Projects Reporting Progress:3
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 11.639 | 5.241 | 2.46 | 6
Progress | 1.74 | 1.7 | 1.282 | 2
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 84
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Prakachik Khows Canal | 0.46 | 0 | 0 | 0.219 | 0.219 | 47.40 | 0.243
2. | Tral Lift Irrigation Project | 1.41 | 0 | 0 | 0.5 | 0.5 | 35.39 | 0.913
3. | Rajpora Lift Irrigation Project | 0.59 | 0 | 0 | 0.563 | 0.563 | 96.24 | 0.022
 | TOTAL | 2.46 | 0 | 0 | 1.282 | 1.282 | 52.11 | 1.178
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 85
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Prakachik Khows Canal | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. | Tral Lift Irrigation Project | 3 | 0 | 0 | 0 | 1 | 1 | 33.33 | 2
3. | Rajpora Lift Irrigation Project | 2 | 0 | 0 | 0 | 1 | 1 | 50.00 | 1
 | TOTAL | 6 | 0 | 0 | 0 | 2 | 2 | 33.33 | 3
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 86
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Prakachik Khows Canal | 0.709 | 0 | 0 | 0.21 | 0.21 | 29.619 | 0.49
2. | Tral Lift Irrigation Project | 3.011 | 0 | 0 | 0.64 | 0.64 | 21.255 | 0.237
3. | Rajpora Lift Irrigation Project | 1.521 | 0 | 0 | 0.85 | 0.85 | 55.884 | 0.67
 | TOTAL | 5.241 | 0 | 0 | 1.70 | 1.70 | 32.437 | 1.397
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Note:- Central assistance (CA) released at the fag end of financial year, 2018-19 not received by executing agency yet.

## Slide 87
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Prakachik Khows Canal | 1.866 | 0 | 0 | 0 | 0 | 0.00 | 1.87
2. | Tral Lift Irrigation Project | 6.161 | 0 | 0 | 1.05 (SS) | 1.05 | 17.04 | 5.11
3. | Rajpora Lift Irrigation Project | 3.613 | 0 | 0 | .69 (SS) | 0.69 | 19.10 | 2.92
 | TOTAL | 11.64 | 0 | 0 | 1.74 | 1.74 | 14.95 | 9.90
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Note:- Central assistance (CA) released at the fag end of financial year, 2018-19 not received by executing agency yet.

## Slide 88
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Prakachik Khows Canal | 0.462 | 0 | 0.219 | 0.219 | 47.40 | 2.26 | 1.25 | 55.31
2. | Tral Lift Irrigation Project | 3.415 | 2.002 | 0.5 | 2.502 | 73.27 | 6 | 4.44 | 74.00
3. | Rajpora Lift Irrigation Project | 1.62 | 1.035 | 0.563 | 1.598 | 98.64 | 2.43 | 2.43 | 100.00
 | TOTAL | 5.497 | 3.037 | 1.282 | 4.319 | 78.57 | 10.69 | 8.12 | 75.96
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 89
Glimpses Of Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
JAMMU AND KASHMIR

## Slide 90
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified). : Central assistance (CA) released at the fag end of financial year, 2018-19 not received by executing agency yet to be utilized.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 91
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{....Present Project-specific information and Issues}
Extra Slides

## Slide 92
Jharkhand
Number of Projects : 1 Projects Included: 1 Projects Availing CA: 0 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 747.53 | 133.32 | 66.645 | 256
Progress | 0 | 0 | 0 | 0
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 93
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Subarnarekha Multipurpose | 66.645 | 0 | 0 | 0 | 0 | 0 | 13.33
 | TOTAL | 66.645 | 0 | 0 | 0 | 0 | 0 | 13.33
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 94
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Subarnarekha Multipurpose | 256 | 0 | 0 | 0 |  | 0 | 0 | 106
 | TOTAL | 256 | 0 | 0 | 0 |  | 0 | 0 | 106
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 95
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Subarnarekha Multipurpose | 133.32 | 0 | 0 | 0 | 0 | 0 | 149.50
 | TOTAL | 133.32 | 0 | 0 | 0 | 0 | 0 | 149.50
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 96
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Subarnarekha Multipurpose | 747.53 | 0 | 0 | 0 | 0 | 0 | 149.50
 | TOTAL | 747.53 | 0 | 0 | 0 | 0 | 0 | 149.50
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 97
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Subarnarekha Multipurpose | 66.645 | 0 | 0 | 0 | 0 | 236.85 | 107.33 | 45.31
 | TOTAL | 66.645 | 0 | 0 | 0 | 0 | 236.85 | 107.33 | 45.31
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 98
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 99
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Thirty two no's IR and DPR of CADWM work of CLMC has been prepared by consultant M/S WAPCOS amounting to Rs 107.52 Cr. One no of UGPL work amounting to Rs 147.65 Lakh is in progress (OR-36 Ex K.M 80.78 of CLMC). Work of 2 no's CADWM work of OR-37 and OR -39 amounting to Rs 218.45 Lakh & Rs 988.92 Lakh respectively (Total Rs 12.07 Cr) has been tendered, which will be decided by the first week of June19.
IR and DPR of CADWM work of GLMC amounting to Rs 62.15 Cr has been prepared by consultant M/S WAPCOS. Certain queries have been asked by CE, LGBO, Patna and Monitoring & Evaluation Directorate, CWC, Ranchi which has been complied.
Six no’s of IR & DPR of CADWM work of GLMC amounting to Rs 12.34 Cr has been prepared
Extra Slides

## Slide 100
KARNATAKA
Number of Projects : 5 Projects Included : 5 Projects Availing CA: 4 Projects Reporting Progress : 4
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 1012.17 | 179.88 | 84.02 | 807
Progress | 113 | 60.16 | 30.93 | 235

## Slide 101
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bhīma LIS | 12.9 | 3.396 | 5.373 | 2.754 | 11.52 | 89.33 | 1.375
2. | Upper Tunga Irrigation Project (Project extends beyond 2019-20) | 25.45 | 2.828 | 4.287 | 2.119 | 9.234 | 36.28 | 5
3. | Karanja | 5.588 | 0 | 0.547 | 0.758 | 1.305 | 23.35 | 4.283
4. | Narayana Left Bank Canal System (NLBC) - ERM | 28.67 | 0 | 0 | 0 | 0 | 0 | 0
5. | Sri Rameswar Lift Irrigation Scheme | 11.42 | 4.857 | 1.294 | 2.715 | 8.866 | 77.64 | 0.515
 | TOTAL | 84.03 | 11.08 | 11.50 | 8.346 | 30.93 | 36.81 | 11.17
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 102
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bhīma LIS | 47 | 0 | 0 | 38 | 2 | 40 | 85.11 | 7
2. | Upper Tunga Irrigation Project (Project extends beyond 2019-20) | 186 | 0 | 0 | 48 | 66 | 114 | 61.29 | 34
3. | Karanja | 51 | 0 | 45 | 3 | 3 | 51 | 100 | 0
4. | Narayana Left Bank Canal System (NLBC) - ERM | 501 | 0 | 0 | 0 | 14 | 14 | 2.79 | 487
5. | Sri Rameswar Lift Irrigation Scheme | 22 | 0 | 1 | 9 | 6 | 16 | 72.73 | 6
 | TOTAL | 807 | 0 | 46 | 98 | 91 | 235 | 29.12 | 534
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 103
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bhīma LIS | 23.63 | 0 | 12.74 | 5.09 | 17.83 | 75.45 | 4.125
2. | Upper Tunga Irrigation Project (Project extends beyond 2019-20) | 59.86 | 21.04 | 0 | 0 | 21.04 | 35.15 | 8.31
3. | Karanja | 11.23 | 0 | 0 | 4.53 | 4.53 | 40.34 | 9.77
4. | Narayana Left Bank Canal System (NLBC) - ERM | 62.17 | 0 | 0 | 0 | 0 | 0 | 0
5. | Sri Rameswar Lift Irrigation Scheme | 22.99 | 10.38 | 2.51 | 3.87 | 16.76 | 72.90 | 1.09
 | TOTAL | 179.9 | 31.42 | 15.25 | 13.49 | 60.16 | 33.44 | 23.295
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 104
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bhīma LIS | 56.56 | 10.87 | 17.91 | 5.45 | 34.23 | 60.52 | 8.17
2. | Upper Tunga Irrigation Project (Project extends beyond 2019-20) | 116.28 | 5.93 | 13.71 | 14.21 | 33.85 | 29.11 | 16.36
3. | Karanja | 42.6 | 0 | 1.88 | 1.52 | 3.4 | 7.98 | 37.78
4. | Narayana Left Bank Canal System (NLBC) - ERM | 750 | 0 | 0 | 0 | 0 | 0 | 0
5. | Sri Rameswar Lift Irrigation Scheme | 46.73 | 22.14 | 8.14 | 11.26 | 41.54 | 88.89 | 2.01
 | TOTAL | 1,012.17 | 38.94 | 41.64 | 32.44 | 113 | 11.17 | 64.32
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 105
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Bhīma LIS | 24.292 | 11.39 | 11.52 | 22.91 | 94.31 | 24.29 | 24.29 | 100
2. | Upper Tunga Irrigation Project (Project extends beyond 2019-20) | 80.494 | 55.05 | 9.234 | 64.284 | 79.86 | 80.49 | 72.9 | 90.57
3. | Karanja | 29.227 | 22.11 | 1.305 | 23.415 | 80.11 | 29.23 | 25.83 | 88.37
4. | Narayana Left Bank Canal System (NLBC) - ERM | 28.67 | 0 | 0 | 0 | 0 | 105 | 104.4 | 99.43
5. | Sri Rameswar Lift Irrigation Scheme | 13.8 | 2.382 | 8.866 | 11.248 | 81.51 | 13.8 | 13.8 | 100
 | TOTAL | 176.48 | 90.932 | 30.925 | 121.86 | 69.05 | 252.81 | 241.22 | 95.42
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
*i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.
**Out of 29.227 Ha CCA, 1.526Ha of CCA is dropped from the scope of project

## Slide 106
Glimpses Of Project Progress: Photographs of Bhima Lift Irrigation Scheme
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
BLIS-Construction of FIC
BLIS-Construction of FIC

## Slide 107
Glimpses Of Project Progress: Photographs of Sri Rameshwara LIS
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Construction of FIC under Bagojikoppa Main Canal
Jackwell cum pump house of Sri Rameshwara LIS at Aralimatti Village, Gokak Taluk

## Slide 108
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet: At present there are no such issues reported
X | Delay in Govt/Administrative clearances: NLBC
X | State budget constraints: No issues
√ | Unwillingness of farmers: Under Sri Rameshwara LIS , as the farmers have made there own arrangements to irrigate the land, Farmers are not allowing to create FIC in an extent 487 Ha
X | Delays in tendering: No issues
X | Capacity related issues of Implementing Agencies: No issues
X | Capacity related issues of Contractors/Suppliers: No issues
X | Other Issue (to be specified) : Under Sri Rameshwara LIS, in the remaining 28 Ha, as there is change of land use, construction activity can be treated as almost complete.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 109
THANK YOU

## Slide 110
Kerala
Number of Projects : 2 Projects Included: 1 Projects Availing CA: 0 Projects Reporting Progress:1
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 107.29 | 48.71 | 17.245 | 240
Progress | 1.54 | 0 | 0 | 114
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 111
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Muvattupuzha | 17.245 | 0 | 0 | 0 | 0 | 0 | 2.4
 | TOTAL | 17.245 | 0 | 0 | 0 | 0 | 0 | 2.4
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 112
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Muvattupuzha | 240 | 95 | 0 | 0 | 19 | 114 | 47.5 | 32
 | TOTAL | 240 | 95 | 0 | 0 | 19 | 114 | 47.5 | 32
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 113
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Muvattupuzha | 48.71 | 0 | 0 | 0 | 0 | 0 | 4
 | TOTAL | 48.71 | 0 | 0 | 0 | 0 | 0 | 4
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 114
Total Expenditure Progress
Sl. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Muvattupuzha | 107.29 | 1.54 | 0 | 0 | 1.54 | 1.44 | 8.00
 | TOTAL | 107.29 | 1.54 | 0.00 | 0.00 | 1.54 | 1.44 | 8.00
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 115
Broad Review
Sl. No | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Muvattupuzha | 19.237 | 1.992 | 0 | 1.992 | 10.355 | 30.719 | 27.824 | 90.576
 | TOTAL | 19.237 | 1.992 | 0.000 | 1.992 | 10.355 | 30.719 | 27.824 | 90.576
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 116
Glimpses Of Project Progress

## Slide 117
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 118
Key Reasons For Progress Delays
 | Other Issues
1. | Muvattupuzha Valley Irrigation Project passing through Ghat areas. Due to the undulated topography, 100% efficiency can not be attained, as per the present norms of CADWM
2. | High labour cost.
3. | Changes in the climatic conditions and cropping pattern.
4. | As the value of land is high in this region, people are not willing to surrender land at free of cost.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 119
MADHYA PRADESH
Number of Projects : 14 Projects Included: 14 Projects Availing CA: 14 Projects Reporting Progress:14
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 2345.39 | 1242.48 | 635.13 | 437
Progress | 618.35 | 251.45 | 210.04 | 351
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 120
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bargi Diversion Project Phase-I | 21.19 | 0 | 0 | 0 | 0 | 0 | 
2. | Indira Sagar Project Canal Phase - I & II | 11.77 | 0.78 | 2.12 | 0.95 | 3.85 | 32.71 | 
3. | Indira Sagar Project Canal Phase - III | 23.49 | 0.42 | 0.63 | 0.41 | 1.46 | 6.22 | 18.75
4. | Omkareshwar Project Canal Phase-IV | 54.62 | 0 | 0 | 0 | 0.00 | 0 | 15.5
5. | Sindh Project Phase II | 90.56 | 28.3 | 29.27 | 9.18 | 66.75 | 73.71 | 6.05
6. | Bansagar Unit 2 | 97.04 | 19.36 | 15.17 | 10.96 | 45.49 | 46.88 | 8.14
7. | Bargi Diversion Project Phase – II | 31.9 | 0 | 0 | 0 | 0 | 0 | 
8. | Bargi Diversion Project Phase III | 26 | 0 | 0 | 0 | 0 | 0 | 
9. | Bargi Diversion Project Phase IV | 34 | 0 | 0 | 0 | 0 | 0 | 
10. | Barriyarpur LBC | 19 | 4.99 | 3.39 | 0.6 | 8.97 | 47.21 | 1.71
11. | Indira Sagar Project Canal Ph IV | 19.6 | 0 | 0 | 0 | 0 | 0 | 3
12. | Indira Sagar Project Canal Ph - V | 33.14 | 0.24 | 0.5 | 0.24 | 0.97 | 2.93 | 32.17
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
CCA Progress

## Slide 121
CCA Progress-Contd..
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
13. | Mahan Project | 14.31 | 2.23 | 5.03 | 0 | 7.26 | 50.73 | 1.33
14. | Mahi Project | 28.13 | 1.06 | 6.07 | 4.66 | 11.78 | 41.88 | 5.25
15. | Mahuar Project | 9.16 | 5.96 | 2.25 | 0 | 8.21 | 89.63 | 0
16. | Omkareshwar Project Canal Phase-II | 19.57 | 3.07 | 2.45 | 0.7 | 9.88 | 50.49 | 9.69
17. | Omkareshwar Project Canal Phase-III | 48.59 | 0 | 3.87 | 6.94 | 10.80 | 22.23 | 11.2
18. | Pench Project | 28.07 | 5.83 | 5.19 | 3.19 | 14.21 | 50.62 | 4.38
19. | Sagad Project | 9.48 | 1.16 | 2.7 | 4.58 | 8.43 | 88.92 | 0.37
20. | Sanjay Sagar (Bah) Project | 9.67 | 1.04 | 1.36 | 4.47 | 6.86 | 70.94 | 0.76
21. | Singhpur Project | 5.84 | 1.89 | 3.23 | 0 | 5.12 | 87.67 | 0.19
 | TOTAL | 635.13 | 76.33 | 83.23 | 46.88 | 210.04 | 33.07 | 118.49
( Area in Th. Ha.)
MADHYA PRADESH
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 122
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bargi Diversion Project Phase-I | 14 | 14 | 0 | 0 | 0 | 14 | 100 | 0
2. | Indira Sagar Project Canal Phase - I & II | 58 | 23 | 0 | 0 | 0 | 23 | 39.66 | 0
3. | Indira Sagar Project Canal Phase - III | 20 | 4 | 0 | 0 | 0 | 4 | 20 | 9
4. | Omkareshwar Project Canal Phase-IV | 29 | 0 | 0 | 14 | 0 | 14 | 48.28 | 0
5. | Sindh Project Phase II | 54 | 52 | 2 | 0 | 0 | 54 | 100 | 0
6. | Bansagar Unit 2 | 74 | 55 | 19 | 0 | 0 | 74 | 100 | 0
7. | Bargi Diversion Project Phase – II | 15 | 13 | 0 | 1 | 0 | 14 | 93 | 0
8. | Barriyarpur LBC | 23 | 23 | 0 | 0 | 0 | 23 | 100 | 0
9. | Indira Sagar Project Canal Phase – IV | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10
10. | Indira Sagar Project Canal Phase - V | 17 | 5 | 0 | 0 | 0 | 5 | 29 | 12
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
WUA Progress

## Slide 123
WUA Progress-Contd..
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
11. | Mahan Project | 10 | 10 | 0 | 0 | 0 | 10 | 100 | 
12. | Mahi Project | 18 | 12 | 6 | 0 | 0 | 18 | 100 | 
13. | Mahuar Project | 7 | 10 | 0 | 0 | 0 | 10 | 143 | 
14. | Omkareshwar Project Canal Phase-II | 10 | 0 | 0 | 0 | 0 | 10 | 100 | 
15. | Omkareshwar Project Canal Phase-III | 28 | 28 | 0 | 0 | 0.00 | 28 | 100 | 
16. | Pench Project | 37 | 24 | 13 | 0 | 0 | 37 | 100 | 
17. | Sagad Project | 4 | 4 | 0 | 0 | 0 | 4 | 100 | 
18. | Sanjay Sagar (Bah) Project | 4 | 4 | 0 | 0 | 0 | 4 | 100 | 
19. | Singhpur Project | 5 | 5 | 0 | 0 | 0 | 5 | 100 | 
20. | Bargi Diversion Project Phase – III | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 
21. | Bargi Diversion Project Phase – IV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 
 | TOTAL | 437 | 286 | 40 | 15 | 0 | 351 | 80.32 | 31
(WUA’s in No’s)
MADHYA PRADESH
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 124
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bargi Diversion Project Phase-I | 41.18 | 0 | 0 | 5.98 | 5.98 | 14.52 | 
2. | Indira Sagar Project Canal Phase - I,II,III,IV & V | 196.72 | 6.64 | 0 | 0 | 6.64 | 3.38 | 
3. | Omkareshwar Project Canal Phase-II,III & IV | 306.92 | 9.61 | 0 | 0 | 9.61 | 3.13 | 
4. | Sindh Project Phase II | 180.76 | 17.19 | 43.31 | 14.29 | 74.79 | 41.38 | 
5. | Bansagar Unit 2 | 224.30 | 22.35 | 15.97 | 18.24 | 56.56 | 25.22 | 
6. | Bargi Diversion Project Phase - II | 60.87 | 0.00 | 0.00 | 8.96 | 8.96 | 14.72 | 
7. | Barriyarpur LBC | 25.93 | 7.14 | 3.97 | 4.99 | 16.10 | 62.08 | 
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 125
CA Release Progress-Contd…
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
8. | Mahan Project | 27.26 | 2.14 | 6.38 | 3.09 | 11.61 | 42.59 | 0
9. | Mahi Project | 64.28 | 2.34 | 8.72 | 6.05 | 17.11 | 26.61 | 0
10. | Mahuar Project | 16.80 | 2.92 | 5.28 | 0.60 | 8.80 | 52.41 | 0
11. | Pench Project | 51.22 | 5.35 | 8.60 | 5.90 | 19.85 | 38.76 | 0
12. | Sagad Project | 17.68 | 0 | 4.34 | 2.15 | 6.49 | 36.69 | 0
13. | Sanjay Sagar (Bah) Project | 18.09 | 0 | 4.02 | 0.00 | 4.02 | 22.23 | 0
14. | Singhpur Project | 10.37 | 2.06 | 2.20 | 0.66 | 4.92 | 47.50 | 0
 | TOTAL | 1242.48 | 77.74 | 102.80 | 70.91 | 251.40 | 20.24 | 0
(CA in Rs. Crores)
MADHYA PRADESH
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 126
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bargi Diversion Project Phase-I | 82.52 | 0 | 0 | 0 | 0 | 0 | 
2. | Indira Sagar Project Canal Phase - I & II | 29.42 | 1.95 | 5.30 | 2.37 | 9.62 | 32.70 | 
3. | Indira Sagar Project Canal Phase - III | 58.72 | 1.06 | 1.57 | 1.02 | 3.65 | 6.22 | 50.76
4. | Omkareshwar Project Canal Phase-IV | 326.65 | 0 | 0 | 0 | 0 | 0 | 
5. | Sindh Project Phase II | 361.53 | 70.00 | 166.80 | 26.97 | 263.77 | 72.96 | 19.10
6. | Bansagar Unit 2 | 448.60 | 49.01 | 38.53 | 27.94 | 115.48 | 25.74 | 22.00
7. | Bargi Diversion Project Ph – II | 121.99 | 0 | 0 | 0 | 0 | 0 | 
8. | Barriyarpur LBC | 51.85 | 12.68 | 8.57 | 1.53 | 22.79 | 43.95 | 5.30
9. | Indira Sagar Project Canal Ph – IV | 49.00 | 0 | 0 | 0 | 0 | 0 | 
10. | Indira Sagar Project Canal Ph - V | 165.70 | 1.18 | 2.49 | 1.18 | 4.84 | 2.92 | 123.97
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 127
Total Expenditure Progress-Contd..
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
11. | Mahan Project | 54.52 | 5.59 | 17.60 | 0.11 | 23.30 | 42.74 | 3.64
12. | Mahi Project | 128.34 | 2.66 | 15.79 | 11.39 | 29.84 | 23.25 | 14.34
13. | Mahuar Project | 33.60 | 16.06 | 7.18 | 1.06 | 24.30 | 72.34 | 1.04
14. | Omkareshwar Project Canal Phase-II | 68.19 | 4.63 | 3.70 | 1.75 | 10.08 | 14.078 | 
15. | Omkareshwar Project Canal Ph-III | 169.37 | 0.00 | 9.17 | 13.15 | 22.32 | 13.18 | 
16. | Pench Project | 102.44 | 14.61 | 13.02 | 9.07 | 36.70 | 35.82 | 12.49
17. | Sagad Project | 35.37 | 2.92 | 7.03 | 11.77 | 21.72 | 61.41 | 
18. | Sanjay Sagar (Bah) Project | 36.19 | 2.61 | 3.40 | 11.10 | 17.11 | 47.26 | 2.53
19. | Singhpur Project | 21.39 | 4.73 | 8.10 | 0.00 | 12.83 | 59.98 | 
20. | Bargi Diversion Project Ph – III | 0 | 0 | 0 | 0 | 0 | 0 | 
21. | Bargi Diversion Project Ph – IV | 0 | 0 | 0 | 0 | 0 | 0 | 
 | TOTAL | 2345.39 | 189.69 | 308.25 | 120.41 | 618.35 | 26.36 | 131.20
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 128
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Bargi Diversion Project Phase-I | 22.587 | 1.39 | 0 | 1.39 | 6.15 | 34.12 | 20.09 | 58.88
2. | Indira Sagar Proj Canal Ph I & II | 11.77 | 2.475 | 3.85 | 6.325 | 53.74 | 62.2 | 62.2 | 100
3. | Indira Sagar Proj Canal Ph III | 23.49 | 0.812 | 1.46 | 2.272 | 9.67 | 16 | 16.68 | 104.25
4. | Omkareshwar Proj Canal Ph-IV | 54.63 | 3.435 | 0.00 | 3.435 | 6.29 | 54.63 | 54.63 | 100
5. | Sindh Project Phase II | 98.25 | 7.69 | 66.75 | 74.44 | 75.77 | 162.1 | 162.1 | 100
6. | Bansagar Unit 2 | 154.69 | 57.65 | 45.49 | 103.14 | 66.68 | 154.54 | 154.54 | 100
7. | Bargi Diversion Project Phase - II | 31.9 | 0 | 0 | 0 | 0 | 51.36 | 41.63 | 81.06
8. | Barriyarpur LBC | 38.99 | 19.99 | 8.97 | 28.96 | 74.28 | 43.85 | 43.85 | 100
9. | Indira Sagar Proj Canal Ph IV | 19.6 | 0 | 0.00 | 0 | 0.00 | 27.05 | 8.5 | 31.42
10. | Indira Sagar Project Canal Ph - V | 33.14 | 0.968 | 0.97 | 1.938 | 5.85 | 33.14 | 32 | 96.56
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 129
Broad Review-Contd
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
11. | Mahan Project | 16.15 | 1.84 | 7.26 | 9.1 | 56.35 | 19.74 | 16.89 | 85.56
12. | Mahi Project | 28.13 | 0 | 11.78 | 11.78 | 41.88 | 33.75 | 26.07 | 77.24
13. | Mahuar Project | 9.5 | 0.34 | 8.21 | 8.55 | 90.00 | 13.78 | 13.78 | 100
14. | OSP Proj Canal Ph-II | 19.58 | 4.61 | 9.88 | 14.49 | 74.00 | 19.58 | 15.8 | 80.69
15. | OSP Proj Canal Ph-III | 48.59 | 0 | 10.80 | 10.8 | 22.23 | 48.59 | 40.75 | 83.86
16. | Pench Project | 28.07 | 0.2 | 14.21 | 14.41 | 51.34 | 28.27 | 21.27 | 75.24
17. | Sagad Project | 9.48 | 0 | 8.43 | 8.43 | 88.92 | 17.06 | 17.06 | 100
18. | Sanjay Sagar (Bah) Project | 9.89 | 0.22 | 6.86 | 7.08 | 71.59 | 17.81 | 17.81 | 100
19. | Singhpur Project | 6 | 0.16 | 5.12 | 5.28 | 88.00 | 10.2 | 10.2 | 100
20. | Bargi Diversion Proj Ph – III | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. | Bargi Diversion Proj Ph – IV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | TOTAL | 664.44 | 101.78 | 210.04 | 311.82 | 46.93 | 847.77 | 775.85 | 91.52
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 130
Glimpses Of Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 132
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
√ | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 133
MAHARASHTRA
Number of Projects : 22 Projects Included: 22 Projects Availing CA: 18 Projects Reporting Progress:17
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 2066 | 983.39 | 517.4 | 1689
Progress | 156.4 | 73.77 | 57.878 | 841
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 134
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bawanthadi (IS) | 2.5 | 0 | 0.3 | 1.04 | 1.34 | 53.6 | 1.16
2. | Lower Dudhna | 30.04 | 0 | 0 | 6.127 | 6.127 | 20.4 | 8.9
3. | Lower Panzara | 6.785 | 0 | 0 | 2.911 | 2.911 | 42.9 | 3.874
4. | Lower Wardha | 62.45 | 2.516 | 14.272 | 8.192 | 24.98 | 40 | 15
5. | Nandur Madhmeshwar Ph-II | 23.12 | 0.055 | 0.735 | 0.052 | 0.842 | 3.642 | 1
6. | Tillari' | 6.68 | 0 | 0 | 0 | 0 | 0 | 0.32
7. | Waghur | 17.97 | 0.423 | 0 | 5.83 | 6.253 | 34.79 | 11.72
8. | Arjuna | 5.708 | 0 | 0 | 0 | 0 | 0 | 0.1
9. | Aruna | 5.942 | 0 | 0 | 0 | 0 | 0 | 0.1
10. | Bembla | 29.78 | 0.085 | 2.221 | 3.504 | 5.81 | 19.51 | 5
11. | Dhom Balaakwadi | 18.1 | 0 | 0 | 1.559 | 1.559 | 8.613 | 0.32
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 135
CCA Progress-Contd..
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
12. | Gadnadi | 3.12 | 0 | 0 | 0.426 | 0.426 | 13.65 | 0.1
13. | Gosikhurd (NP) | 176.1 | 0 | 0 | 0 | 0 | 0 | 25
14. | Khadakpurna | 15.72 | 1.937 | 0.053 | 0.771 | 2.761 | 17.56 | 0.32
15. | Krishna Koyana Lift Irrigation Project | 52.82 | 0 | 0 | 0 | 0 | 0 | 5
16. | Kudali Medium Project | 6.068 | 0 | 0 | 0 | 0 | 0 | 0.2
17. | Lower Pedhi | 10.2 | 0 | 0 | 0 | 0 | 0 | 0
18. | Morna (Gureghar) | 4.229 | 0 | 0 | 0 | 0 | 0 | 0.15
19. | Sangola Branch Canal | 6.883 | 0 | 0 | 0.149 | 0.149 | 2.165 | 0.4
20. | Tarali | 13.09 | 0 | 0 | 0 | 0 | 0 | 0.24
21. | Upper Kundalika | 2.8 | 0 | 0 | 2.3 | 2.3 | 82.14 | 0.6
22. | Upper Pen Ganga | 17.29 | 0 | 1.093 | 1.327 | 2.42 | 14 | 1
 | Total | 517.4 | 5.269 | 18.421 | 34.19 | 57.878 | 11.19 | 80.5
( Area in Th. Ha.)
MAHARASHTRA
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 136
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bawanthadi (IS) | 60 | 0 | 0 | 0 | 0 | 0 | 0.00 | 60
2. | Lower Dudhna | 72 | 0 | 22 | 0 | 39 | 61 | 84.72 | 11
3. | Lower Panzara | 15 | 0 | 0 | 0 | 15 | 15 | 100.00 | 0
4. | Lower Wardha | 138 | 0 | 98 | 0 | 12 | 110 | 79.71 | 28
5. | Nandur Madhmeshwar Ph-II | 121 | 0 | 115 | 0 | 0 | 115 | 95.04 | 6
6. | Tillari' | 18 | 0 | 8 | 0 | 7 | 15 | 83.33 | 3
7. | Waghur | 78 | 0 | 6 | 0 | 15 | 21 | 26.92 | 25
8. | Arjuna | 12 | 0 | 1 | 0 | 0 | 1 | 8.33 | 5.00
9. | Aruna | 16 | 0 | 0 | 0 | 0 | 0 | 0.00 | 5
10. | Bembla | 175 | 0 | 113 | 0 | 20 | 133 | 76.00 | 30
11. | Dhom Balaakwadi | 85 | 0 | 44 | 0 | 0 | 44 | 51.76 | 20
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
WUA Progress

## Slide 137
WUA Progress-Contd..
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
12. | Gadnadi | 7 | 0 | 0 | 0 | 0 | 0 | 0.00 | 3
13. | Gosikhurd (NP) | 387 | 0 | 82 | 0 | 0 | 82 | 21.19 | 100
14. | Khadakpurna | 66 | 0 | 45 | 0 | 0 | 45 | 68.18 | 10
15. | Krishna Koyana Lift Irrigation Project | 237 | 0 | 80 | 0 | 63 | 143 | 60.34 | 50
16. | Kudali Medium Project | 13 | 0 | 0 | 0 | 0 | 0 | 0.00 | 5
17. | Lower Pedhi | 30 | 0 | 0 | 0 | 0 | 0 | 0.00 | 10
18. | Morna (Gureghar) | 18 | 0 | 0 | 0 | 0 | 0 | 0.00 | 5
19. | Sangola Br. Canal | 40 | 0 | 6 | 0 | 22 | 28 | 70.00 | 5
20. | Tarali | 48 | 0 | 5 | 0 | 0 | 5 | 10.42 | 10
21. | Upper Kundalika | 7 | 0 | 0 | 0 | 0 | 0 | 0.00 | 7
22. | Upper Pen Ganga | 46 | 0 | 23 | 0 | 0 | 23 | 50.00 | 10
 | Total | 1689 | 0 | 648 | 0 | 193 | 841 | 49.79 | 408
(WUA’s in No’s)
MAHARASHTRA
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 138
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bawanthadi (IS) | 7.82 | 0 | 0.52 | 0 | 0.52 | 6.31 | 2.82
2. | Lower Dudhna | 72.74 | 0 | 8.1 | 0 | 8.1 | 11.2 | 9.5
3. | Lower Panzara | 14.51 | 0 | 2.15 | 3.97 | 6.12 | 38.9 | 4
4. | Lower Wardha | 100.43 | 15.2 | 0 | 5.46 | 20.6 | 20.9 | 15
5. | Nandur Madhmeshwar Ph-II | 49.21 | 0 | 0 | 0 | 0 | 0 | 2.5
6. | Tillari' | 16.21 | 0 | 1.81 | 0 | 1.81 | 13.8 | 4
7. | Waghur | 39.02 | 0 | 1.57 | 0 | 1.57 | 4.01 | 6.67
8. | Arjuna | 11.28 | 0 | 0.8 | 0 | 0.8 | 7.21 | 0.78
9. | Aruna | 9.52 | 0 | 0 | 0 | 0 | 0 | 0.66
10. | Bembla | 57.55 | 0 | 5.99 | 3.51 | 9.5 | 14.7 | 5.25
11. | Dhom Balaakwadi | 9.23 | 0 | 0 | 1.82 | 1.82 | 22.3 | 4
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
CA Release Progress

## Slide 139
CA Release Progress-Contd..
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
12. | Gadnadi | 6.12 | 0 | 0.03 | 0 | 0.03 | 0.49 | 0.32
13. | Gosikhurd (NP) | 371.86 | 0 | 0 | 9.38 | 9.38 | 2.65 | 16
14. | Khadakpurna | 31.77 | 0 | 2.65 | 0 | 2.65 | 8.47 | 3.2
15. | Krishna Koyana Lift Irrigation Project | 67.67 | 0 | 3.81 | 0 | 3.81 | 5.66 | 9.18
16. | Kudali Medium Project | 10.07 | 0 | 0 | 0 | 0 | 0 | 1.2
17. | Lower Pedhi | 20.62 | 0 | 0 | 0 | 0 | 0 | 1.88
18. | Morna (Gureghar) | 8.23 | 0 | 0 | 0.28 | 0.28 | 3.43 | 0.49
19. | Sangola Br. Canal | 13.95 | 0 | 0.55 | 1.37 | 1.92 | 13.88 | 4.3
20. | Tarali | 25.21 | 0 | 1.31 | 0 | 1.31 | 5.2 | 2.82
21. | Upper Kundalika | 5.56 | 0 | 0.52 | 0 | 0.52 | 9.29 | 1.9
22. | Upper Pen Ganga | 34.81 | 0 | 3 | 0 | 3 | 8.62 | 4.5
 | Total | 983.39 | 15.17 | 32.81 | 25.79 | 73.77 | 196.9 | 101
(CA in Rs. Crores)
MAHARASHTRA
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 140
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Bawanthadi (IS) | 15.63 | 0 | 0.3 | 1.85 | 2.15 | 13.76 | 6
2. | Lower Dudhna | 145.5 | 0 | 0 | 17.39 | 17.39 | 11.95 | 19
3. | Lower Panzara | 29.02 | 0 | 0.98 | 5.52 | 6.5 | 22.40 | 8
4. | Lower Wardha | 198.6 | 0 | 24.3 | 24.49 | 48.79 | 24.57 | 30
5. | Nandur Madhmeshwar Ph-II | 98.5 | 0 | 1.57 | 0.04 | 1.61 | 1.63 | 5
6. | Tillari' | 32.42 | 0 | 0.84 | 1.75 | 2.59 | 7.99 | 8
7. | Waghur | 77.95 | 0.48 | 0.28 | 30.95 | 31.71 | 40.68 | 13.35
8. | Arjuna | 28.94 | 0 | 0 | 0 | 0 | 0 | 2
9. | Aruna | 20.25 | 0 | 0 | 0 | 0 | 0 | 1.7
10. | Bembla | 164.4 | 0.84 | 8.54 | 14.87 | 24.25 | 14.75 | 15
11. | Dhom Balaakwadi | 21.77 | 0 | 0 | 2.54 | 2.54 | 11.67 | 8
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Total Expenditure Progress

## Slide 141
Total Expenditure Progress-Contd..
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
12. | Gadnadi | 19.12 | 0 | 0 | 0 | 0 | 0.00 | 1
13. | Gosikhurd (NP) | 743.7 | 0 | 0 | 0 | 0 | 0.00 | 32
14. | Khadakpurna | 79.42 | 0 | 0.44 | 0.75 | 1.19 | 1.50 | 8
15. | Krishna Koyana Lift Irrigation Project | 132.7 | 0 | 0 | 0.26 | 0.26 | 0.20 | 18
16. | Kudali Medium Project | 26.75 | 0 | 0 | 0 | 0 | 0.00 | 3
17. | Lower Pedhi | 43.88 | 0 | 0 | 0 | 0 | 0.00 | 4
18. | Morna (Gureghar) | 16.79 | 0 | 0 | 0.3 | 0.3 | 1.79 | 1
19. | Sangola Branch Canal | 32.44 | 0 | 0.58 | 0.56 | 1.14 | 3.51 | 10
20. | Tarali | 53.63 | 0 | 0 | 0 | 0 | 0.00 | 6
21. | Upper Kundalika | 14.62 | 0 | 0 | 6.76 | 6.76 | 46.24 | 5
22. | Upper Pen Ganga | 69.62 | 0 | 3.47 | 5.76 | 9.23 | 13.26 | 9
 | Total | 2066 | 1.32 | 41.3 | 113.8 | 156.4 | 7.57 | 213.05
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 142
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Bawanthadi (IS) | 25.66 | 23.16 | 1.34 | 24.5 | 95.48 | 27.71 | 5.338 | 19.26
2. | Lower Dudhna | 44.48 | 14.44 | 6.127 | 20.57 | 46.24 | 44.48 | 9.264 | 20.83
3. | Lower Panzara | 6.785 | 0 | 2.911 | 2.911 | 42.90 | 6.79 | 3.219 | 47.41
4. | Lower Wardha | 63.33 | 2.13 | 24.98 | 27.11 | 42.81 | 63.33 | 10.03 | 15.83
5. | Nandur Madhmeshwar Ph-II | 52.86 | 29.75 | 0.842 | 30.59 | 57.87 | 20.5 | 2.07 | 10.10
6. | Tillari' | 6.57 | 0 | 0 | 0 | 0.00 | 6.57 | 0.234 | 3.56
7. | Waghur | 17.97 | 0 | 6.253 | 6.253 | 34.80 | 38.57 | 4.62 | 11.98
8. | Arjuna | 5.704 | 0 | 0 | 0 | 0.00 | 5.7 | 0 | 0.00
9. | Aruna | 5.31 | 0 | 0 | 0 | 0.00 | 11.71 | 0 | 0.00
10. | Bembla | 40.17 | 10.39 | 5.81 | 16.2 | 40.33 | 52.54 | 3.09 | 5.88
11. | Dhom Balaakwadi | 18.1 | 14.05 | 1.559 | 15.61 | 86.24 | 18.1 | 1.83 | 10.11
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.
Broad Review

## Slide 143
Broad Review-Contd..
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
12. | Gadnadi | 3.111 | 0 | 0.426 | 0.426 | 13.69 | 3.47 | 0 | 0.00
13. | Gosikhurd (NP) | 190 | 13.89 | 0 | 13.89 | 7.31 | 250.8 | 28.18 | 11.24
14. | Khadakpurna | 23.9 | 8.18 | 2.761 | 10.94 | 45.78 | 22.46 | 2.424 | 10.79
15. | Krishna Koyana Lift Irrigation Project | 52.82 | 0 | 0 | 0 | 0.00 | 104.2 | 1.25 | 1.20
16. | Kudali Medium Proj | 5.327 | 0 | 0 | 0 | 0.00 | 5.33 | 0 | 0.00
17. | Lower Pedhi | 10.19 | 0 | 0 | 0 | 0.00 | 19.3 | 0 | 0.00
18. | Morna (Gureghar) | 4.229 | 0 | 0 | 0 | 0.00 | 3.08 | 0 | 0.00
19. | Sangola Br. Canal | 6.883 | 0 | 0.149 | 0.149 | 2.16 | 11.29 | 0.5 | 4.43
20. | Tarali | 15.83 | 2.744 | 0 | 2.744 | 17.33 | 14.28 | 0 | 0.00
21. | Upper Kundalika | 2.8 | 0 | 2.3 | 2.3 | 82.14 | 2.8 | 1.09 | 38.93
22. | Upper Pen Ganga | 104 | 86.71 | 2.42 | 89.13 | 85.70 | 44.47 | 0.873 | 1.96
 | Total | 706 | 205.4 | 57.88 | 263.3 | 37.30 | 777.5 | 74.01 | 9.52
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 144
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified)- Due to Slow progress of Irrigation Potential creation
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 145
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
Number of Projects included – 22 No. Total Area of Projects (Ha.) – 5,17,397 Ha. a ) Field Channel/PDN -- 4,54,175 Ha. b ) Micro Irrigation -- 62,222 Ha. Total cost of Projects (Cr.) – 2,064.77 Cr. Planning of completion Year Physical (Ha.) Financial (Rs.in Crore) 2017-18 23,690 Ha. (Actual) 94.52 Cr. 2018-19 1,59,161 Ha. 635.05 Cr. 2019-20 2,00,151 Ha. 798.60 Cr. 2020-21 1,34,395 Ha. 536.87 Cr. Total 5,17,397 Ha. 2064.77 Cr.

## Slide 146
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
Budget Provision (Cr.) 2017-18 -- 207.37 Cr. (C.A. 103.21 Cr, State 104.16 Cr.) 2018-19 -- 203.52 Cr. (C.A. 96.15 Cr, State 107.37 Cr.) 2019-20 -- 213.04 Cr. (C.A. 100.97 Cr, State 112.07 Cr.) Central Assistance (C.A.) Release (Cr.) 2015-16 -- 4.54 Cr. 2016-17 -- 15.17 Cr. 2017-18 -- 32.88 Cr. 2018-19 -- 22.60 Cr. Total -- 75.19 Cr. Physical Progress (Ha.) a) Field Channel/PDN Upto 03/2018 -- 23,690 Ha. 04/2018 to 03/2019 -- 28,431 Ha. Total -- 52, 126 Ha. b) Micro Irrigation upto 03/2019 -- 5,752 Ha.

## Slide 147
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Extra Slides
Financial Progress (Cr.)
Upto 03/2018 -- Rs. 42.62 Cr.
04/2018 to 03/2019 -- Rs. 113.79 Cr.
Total -- Rs. 156.41 Cr.
Status of Water User Associations
  a) Total WUA’s -- 1687 Nos. (7,71,413 Ha.)
  b) Registered upto 03/2019 -- 841 Nos. ( 3,32,001 Ha.)
c) Area handed over to WUA’s -- 173 Nos. (61,380 Ha.)

## Slide 148
Manipur
Number of Projects : 2 Projects Included: 2 Projects Availing CA: 0 Projects Reporting Progress:2
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | Balance CCA (in th. Ha.) | WUA (Nos)
Target | 122.712 | 63.655 | 22.036 | 74
Progress | 19.34 | 0 | 5.03 | 34
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 149
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Dolaithabi Barrage | 5.500 | 0 | 1.314 | 0 | 1.314 | 24 | 4.186
2 | Thoubal | 16.536 | 0 | 3.716 | 0 | 3.716 | 23 | 12.820
 | TOTAL | 22.036 | 0 | 5.030 | 0 | 5.030 | 23 | 17.006
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 150
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Dolaithabi Barrage | 19 | 0 | 0 | 11 | 2 | 13 | 68.42 | 6
2 | Thoubal | 55 | 0 | 0 | 18 | 3 | 21 | 38.18 | 34
 | TOTAL | 74 | 0 | 0 | 29 | 5 | 34 | 45.94 | 40
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 151
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Dolaithabi Barrage | 15.887 | 0 | 0 | 0 | 0 | 0 | 11.425
2 | Thoubal | 47.768 | 0 | 0 | 0 | 0 | 0 | 34.650
 | TOTAL | 63.655 | 0 | 0 | 0 | 0 | 0 | 46.075
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 152
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Dolaithabi Barrage | 30.627 | 0 | 5.050 | 0 | 5.050 | 16.5 | 25.577
2 | Thoubal | 92.085 | 0 | 14.290 | 0 | 14.290 | 15.5 | 77.795
 | TOTAL | 122.712 | 0 | 19.340 | 0 | 19.340 | 16 | 103.372
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 153
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Dolaithabi Barrage | 5.50 | 2.28 | 1.31 | 3.59 | 65.29 | 7.54 | 3.29 | 43.63
2 | Thoubal | 16.54 | 6.70 | 3.72 | 10.41 | 62.97 | 29.45 | 17.67 | 60.00
 | TOTAL | 22.04 | 8.97 | 5.03 | 14.00 | 63.55 | 36.99 | 20.96 | 56.66
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 154
Glimpses Of Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
TMP (Ph-III) LSMC
RD No.18.83
Thokchom Loukon,
TMP (Ph-III) LSMC
RD No.19.754
Chakabi Loukon,
Uyun Khunou
TMP (Ph-III) LSMC
RD No.24.469
Khangabok Loukon,

## Slide 155
Glimpses Of Project Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
TMP (Ph-III) RSMC
Arangkot
TMP (Ph-III) RSMC
Changamdabi
TMP (Ph-III) RSMC
Andro Khunjao-1

## Slide 156
Key Reasons For Progress Delays
Status | Key Reason
X | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
√ | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 157
ODISHA
Number of Projects : 8 Projects Included: 8 Projects Availing CA: 8 Projects Reporting Progress:7
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 1265.2 | 420.2 | 236.3 | 545
Progress | 268.9 | 97.49 | 55.17 | 112
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 158
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Upper Indravati Extn. | 23.83 | 5.35 | 18.48 | 0 | 23.83 | 100 | 0
2 | Ret | 8.5 | 0 | 2.417 | 6.083 | 8.5 | 100 | 0
3 | Rukura | 5.75 | 1.377 | 2.88 | 1.333 | 5.59 | 97.22 | 0
4 | Lower Indra | 29.9 | 0 | 0 | 10.02 | 10.02 | 33.51 | 19.88
5 | Telengiri | 9.952 | 0 | 0 | 0.864 | 0.864 | 8.682 | 9.088
6 | Subarnarekha | 68.83 | 2.76 | 1.701 | 0.094 | 4.555 | 6.618 | 5
7 | Ananapur | 60 | 0 | 1.505 | 0.297 | 1.802 | 3.003 | 1.24
8 | Kanupur | 29.58 | 0 | 0 | 0 | 0 | 0 | 0
 | Total | 236.3 | 9.487 | 26.99 | 18.69 | 55.17 | 23.35 | 35.21
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 159
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Upper Indravati Extn. | 59 | 0 | 0 | 59 | 0 | 59 | 100 | 0
2 | Ret | 19 | 0 | 0 | 0 | 19 | 19 | 100 | 0
3 | Rukura | 15 | 0 | 3 | 10 | 2 | 15 | 100 | 0
4 | Lower Indra | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 75
5 | Telengiri | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 22
6 | Subarnarekha | 156 | 0 | 13 | 0 | 6 | 19 | 12.179 | 15
7 | Ananapur | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 12
8 | Kanupur | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Total | 545 | 0 | 16 | 69 | 27 | 112 | 20.55 | 124
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 160
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Upper Indravati Extn. | 44.03 | 8.495 | 30.83 | 0 | 39.32 | 89.31 | 4.709
2 | Ret | 16.55 | 0 | 4.105 | 0 | 4.105 | 24.80 | 12.447
3 | Rukura | 10.21 | 2.41 | 0.802 | 0 | 3.212 | 31.46 | 6.998
4 | Lower Indra | 51.67 | 24.37 | 0 | 0 | 24.37 | 47.16 | 27.301
5 | Telengiri | 16.72 | 0 | 2.838 | 0 | 2.838 | 16.97 | 13.884
6 | Subarnarekha | 126 | 0 | 16.28 | 0 | 16.28 | 12.92 | 20
7 | Ananapur | 101.6 | 0 | 1.82 | 0 | 1.82 | 1.79 | 12
8 | Kanupur | 53.44 | 0 | 1.892 | 3.65 | 5.542 | 10.37 | 10
 | Total | 420.2 | 35.28 | 58.57 | 3.65 | 97.49 | 23.20 | 107.34
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 161
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Upper Indravati Extn. | 140.27 | 43.43 | 65.85 | 13.14 | 122.4 | 87.28 | 12.74
2 | Ret | 46.87 | 0.659 | 8.129 | 28.64 | 37.43 | 79.86 | 3.18
3 | Rukura | 31.71 | 4.82 | 11.06 | 5.118 | 20.99 | 66.20 | 4.71
4 | Lower Indra | 103.08 | 2 | 0 | 39.18 | 41.18 | 39.95 | 61.9
5 | Telengiri | 54.51 | 0 | 0.246 | 6.941 | 7.187 | 13.18 | 47.32
6 | Subarnarekha | 389.58 | 7.846 | 11.95 | 12.98 | 32.78 | 8.41 | 40
7 | Ananapur | 334.37 | 0 | 2.08 | 2.09 | 4.17 | 1.25 | 24
8 | Kanupur | 164.85 | 0 | 1.451 | 1.282 | 2.733 | 1.66 | 20
 | Total | 1265.2 | 58.76 | 100.8 | 109.4 | 268.9 | 21.25 | 213.85
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 162
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Upper Indravati Extn. | 25.48 | 1.65 | 23.83 | 25.48 | 100 | 41.794 | 41.794 | 100
2 | Ret | 8.5 | 0 | 8.423 | 8.42 | 99.06 | 9.775 | 9.728 | 99.52
3 | Rukura | 5.75 | 0 | 5.59 | 5.59 | 97.22 | 7.648 | 6.796 | 88.86
4 | Lower Indra | 29.9 | 0 | 10.02 | 10.02 | 33.51 | 38.87 | 26.502 | 68.18
5 | Telengiri | 9.95 | 0 | 0.864 | 0.86 | 8.643 | 13.789 | 11.815 | 85.68
6 | Subarnarekha | 69.8 | 1.1 | 4.555 | 5.66 | 8.109 | 115.259 | 77.97 | 67.65
7 | Ananapur | 60 | 0 | 1.802 | 1.8 | 3 | 56.72 | 3 | 5.289
8 | Kanupur | 29.58 | 0 | 0 | 0 | 0 | 47.709 | 0 | 0
 | Total | 238.96 | 2.75 | 55.09 | 57.83 | 24.2 | 331.564 | 177.61 | 53.57
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 163
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
√ | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 164
Rajasthan
Number of Projects : 2 Projects Included: 2 Projects Availing CA: 1 Projects Reporting Progress:2
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 220.49 | 115.3 | 43.49 | 2268
Progress | 38.27 | 9.918 | 21.17 | 2251
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 165
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Narmada Canal | 0 | 0 | 0 | 0 | 0 | 0 | 
2 | Mod. of Gang Canal | 43.49 | 6.86 | 7.22 | 7.08 | 21.17 | 48.67 | 9.50
 | TOTAL | 43.49 | 6.86 | 7.22 | 7.08 | 21.17 | 48.67 | 9.50
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 166
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Narmada Canal | 2232 | 2144 | 56 | 1 | 14 | 2215 | 99 | 17
2 | Mod. of Gang Canal | 36 | 36 | 0 | 0 | 0 | 36 | 100 | 0
 | TOTAL | 2268 | 2180 | 56 | 1 | 14 | 2251 | 99 | 17
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 167
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Narmada Canal | 54.06 | 0 | 0 | 0 | 0 | 0 | 11.7
2 | Mod. of Gang Canal | 61.24 | 0 | 2.48 | 7.44 | 9.918 | 16.20 | 19.5
 | TOTAL | 115.3 | 0 | 2.48 | 7.44 | 9.918 | 8.60 | 31.2
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 168
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Narmada Canal | 97.48 | 0 | 0 | 0 | 0 | 0.00 | 19.5
2 | Mod. of Gang Canal | 123.01 | 10.43 | 13 | 14.9 | 38.27 | 31.11 | 39
 | TOTAL | 220.49 | 10.43 | 13 | 14.9 | 38.27 | 17.36 | 58.5
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 169
Broad Review
Sr. No | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Narmada Canal | 246.0 | 246.0 | 0 | 246.0 | 100 | 245.88 | 245.81 | 99.97
2 | Mod. of Gang Canal | 45.694 | 1.389 | 21.17 | 22.6 | 49.36 | 96.51 | 96.51 | 100
 | TOTAL | 291.694 | 247.389 | 21.17 | 269 | 92.07 | 342.39 | 342.32 | 99.98
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 170
Glimpses Of Project Progress
Water course at Chak No 73 NP of Gang Canal Project Phase-II
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 171
Glimpses Of Project Progress
Sprinkler system at Jaisala Distributary of Narmada Canal Project
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{.....Project Photographs (4/5) may be provided}

## Slide 172
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 173
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
{....Present Project-specific information and Issues}
Extra Slides

## Slide 174
TELANGANA
Number of Projects : 11 Projects Included: 11 Projects Availing CA: 9 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 1478.806 | 700.22 | 529.028 | 1148
Progress | 0 | 36.34 | 0 | 0
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 175
CCA Progress
Sr. No. | Project | Balance CCA Target in Th. Ha | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | J. Chokha Rao LIS | 248.685 | 0 | 0 | 0 | 0 | 0 | 33.539
2. | Gollavagu Project | 3.845 | 0 | 0 | 0 | 0 | 0 | 1.538
3. | Mathadivagu Project | 3.44 | 0 | 0 | 0 | 0 | 0 | 1.547
4. | Palemvagu project | 2.014 | 0 | 0 | 0 | 0 | 0 | 1.007
5. | Peddavagu @ Jagannathpur | 6.073 | 0 | 0 | 0 | 0 | 0 | 
6. | Peddavagu @ Neelwai | 5.26 | 0 | 0 | 0 | 0 | 0 | 2.367
7. | Rajiv Bheema L.I. Scheme | 82.153 | 0 | 0 | 0 | 0 | 0 | 30.000
8. | Rallivagu project | 0.918 | 0 | 0 | 0 | 0 | 0 | 0.367
9. | SriKomaram Bheem | 9.915 | 0 | 0 | 0 | 0 | 0 | 4.336
10. | SRSP St.II | 73.138 | 0 | 0 | 0 | 0 | 0 | 61.411
11. | Indiramma Flood Flow Canal | 93.587 | 0 | 0 | 0 | 0 | 0 | 5.669
 | Total | 529.028 | 0 | 0 | 0 | 0 | 0 | 141.781
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 176
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  | Target for 2019-20
 |  |  | Before April 2016 | WUAs Status | 
1 | J. Chokha Rao LIS | 498 | 0 | WUAs shall be formed after completion of the AIBP projects. | 
2. | Gollavagu Project | 8 | 0 |  | 4
3. | Mathadivagu Project | 7 | 0 |  | 3
4. | Palemvagu project | 8 | 0 |  | 
5. | Peddavagu @ Jagannathpur | 15 | 0 |  | 
6. | Peddavagu @ Neelwai | 11 | 0 |  | 
7. | Rajiv Bheema L.I. Scheme | 164 | 0 |  | 
8. | Rallivagu project | 3 | 0 |  | 1
9. | SriKomaram Bheem | 20 | 0 |  | 
10. | SRSP St.II | 356 | 0 |  | 
11. | Indiramma Flood Flow Canal | 58 | 0 |  | 
 | Total | 1148 | 0 |  | 8
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 177
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | J. Chokha Rao LIS | 380.35 | 0 | 10.22 | 0 | 10.22 | 2.69 | 7.04
2. | Gollavagu Project | 7.186 | 0 | 0 | 1.03 | 1.03 | 14.33 | 2.56
3. | Mathadivagu Project | 6.187 | 0 | 0 | 1.8 | 1.8 | 29.09 | 1.28
4. | Palemvagu project | 2.601 | 0 | 0 | 0.51 | 0.51 | 19.60 | 0.35
5. | Peddavagu @ Jagannathpur | 12.20 | 0 | 0 | 0 | 0 | 0.00 | 5.00
6. | Peddavagu @ Neelwai | 6.669 | 0 | 0 | 1.99 | 1.99 | 29.84 | 1.33
7. | Rajiv Bheema L.I. Scheme | 112.22 | 0 | 0 | 0 | 0 | 0.00 | 70.52
8. | Rallivagu project | 1.472 | 0 | 0 | 0.28 | 0.28 | 19.02 | 0.45
9. | SriKomaram Bheem | 19.84 | 0 | 0 | 5.89 | 5.89 | 29.69 | 4.35
10. | SRSP St.II | 103.241 | 0 | 0 | 11.56 | 11.56 | 11.20 | 9.00
11. | Indiramma Flood Flow Canal | 48.26 | 0 | 0 | 3.06 | 3.06 | 6.34 | 2.05
 | Total | 700.22 | 0 | 10.22 | 26.12 | 36.34 | 5.187 | 103.93
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 178
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | J. Chokha Rao LIS | 759.94 | Inclusion on 31st March, 2017 | 0 | 0 | 0 | 0 | 385.725
2. | Gollavagu Project | 20.4 |  | 0 | 0 | 0 | 0 | 10.20
3. | Mathadivagu Project | 12.635 |  | 0 | 0 | 0 | 0 | 6.299
4. | Palemvagu project | 5.2 |  | 0 | 0 | 0 | 0 | 1.729
5. | Peddavagu @ Jagannathpur | 52.5496 |  | 0 | 0 | 0 | 0 | 
6. | Peddavagu @ Neelwai | 25.121 |  | 0 | 0 | 0 | 0 | 9.319
7. | Rajiv Bheema L.I. Scheme | 239.519 |  | 0 | 0 | 0 | 0 | 150.78
8. | Rallivagu project | 5.57 |  | 0 | 0 | 0 | 0 | 2.785
9. | SriKomaram Bheem | 56.546 |  | 0 | 0 | 0 | 0 | 29.519
10. | SRSP St.II | 204.082 |  | 0 | 0 | 0 | 0 | 42.272
11. | Indiramma Flood Flow Canal | 97.23 |  | 0 | 0 | 0 | 0 | 9.396
 | Total | 1478.806 |  | 0 | 0 | 0 | 0 | 648.024
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 179
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2016 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | J. Chokha Rao LIS | 248.685 | 0 | 0 | 0 | 0 | 248.685 | 105.344 | 42.36
2. | Gollavagu Project | 3.845 | 0 | 0 | 0 | 0 | 3.845 | 3.845 | 100
3. | Mathadivagu Project | 3.44 | 0 | 0 | 0 | 0 | 3.440 | 3.44 | 100
4. | Palemvagu project | 2.014 | 0 | 0 | 0 | 0 | 4.100 | 2.077 | 50.65
5. | Peddavagu @ Jagannathpur | 6.073 | 0 | 0 | 0 | 0 | 6.073 | 0 | 0
6. | Peddavagu @ Neelwai | 5.26 | 0 | 0 | 0 | 0 | 5.260 | 3.24 | 61.59
7. | Rajiv Bheema L.I. Scheme | 82.153 | 0 | 0 | 0 | 0 | 82.153 | 59.582 | 72.52
8. | Rallivagu project | 0.918 | 0 | 0 | 0 | 0 | 0.918 | 0.918 | 100
9. | SriKomaram Bheem | 9.915 | 0 | 0 | 0 | 0 | 9.915 | 6.094 | 61.46
10. | SRSP St.II | 73.138 | 0 | 0 | 0 | 0 | 178.066 | 138.372 | 77.70
11. | Indiramma Flood Flow Canal | 93.587 | 0 | 0 | 0 | 0 | 93.587 | 1.214 | 1.29
 | Total | 529.028 | 0 | 0 | 0 | 0 | 636.042 | 324.12 | 60.68
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2016) and before CADWM inclusion.

## Slide 180
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
√ | Delay in Govt/Administrative clearances.
X | State budget constraints.
X | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
√ | Other Issue (to be specified). Due to election process progress is hampered.
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 181
Uttar Pradesh (Greater Sharda Sahayak Command)
Number of Projects : 3 Projects Included: 2 Projects Availing CA: 2 Projects Reporting Progress:0
Chart: Financial Progress
| Total Expenditure (RS Crore) | CA (Rs Crore) | CCA (in th. Ha.) | WUA (Nos)
Target | 1828.1 | 914.92 | 524.38 | 1068
Progress | 0 | 0 | 0 | 0
Physical Progress
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 182
CCA Progress
Sr. No. | Project | Balance CCA Target | CCA Progress |  |  |  |  | Target for 2019-20
 |  |  | 2019-20 | 2020-21 | 2021-22 | Total | % Progress | 
1 | Arjun Sahayak | 44.38 | 0 | 0 | 0 | 0 | 0 | 28.75
2 | Saryu Nahar Ph-III | 480.00 | 0 | 0 | 0 | 0 | 0 | 144
 | TOTAL | 524.38 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 172.75
( Area in Th. Ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 183
WUA Progress
Sr. No. | Project | WUA Target | WUA Progress |  |  |  |  |  | Target for 2019-20
 |  |  | Before April 2016 | 2016-17 | 2017-18 | 2018-19 | Total | % Progress | 
1 | Arjun Sahayak | 108 | 0 | 0 | 0 | 0 | 0 | 0 | .....
2 | Saryu Nahar Ph-III | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 
 | TOTAL | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 
(WUA’s in No’s)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
Note :- Formation of WUA is being done by Irrigation Department (U.P.)

## Slide 184
CA Release Progress
Sr. No. | Project | Overall CA Target | CA Release Progress |  |  |  |  | Target for 2019-20
 |  |  | 2019-20 | 2020-21 | 2021-22 | Total | % Progress | 
1 | Arjun Sahayak | 77.86 | 0 | 0 | 0 | 0 | 0 | 50.05
2 | Saryu Nahar Ph-III | 837.06 | 0 | 0 | 0 | 0 | 0 | 250.26
 | TOTAL | 914.92 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 300.31
(CA in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 185
Total Expenditure Progress
Sr. No. | Project | Total Expenditure Target | Total Expenditure Progress |  |  |  |  | Target for 2019-20
 |  |  | 2019-20 | 2020-21 | 2021-22 | Total | % Progress | 
1 | Arjun Sahayak | 155.37 | 0 | 0 | 0 | 0 | 0 | 100
2 | Saryu Nahar Ph-III | 1672.7 | 0 | 0 | 0 | 0 | 0 | 500
 | TOTAL | 1828.1 | 0 | 0 | 0 | 0 | 0 | 600
(TE in Rs. Crores)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations

## Slide 186
Broad Review
Sr. No. | Project | CADWM |  |  |  |  | AIBP |  | 
 |  | Total CCA of Project | CCA developed before 31.03. 2019 (A)* | Progress in CCA for 99 Priority Projects (B) | Cumulative CCA developed (A+B) | % CCA Progress | Ultimate Irrigation Potential | Potential Created | % IPC
1 | Arjun Sahayak | 44.381 | 0 | 0 | 0 | 0 | 44.4 | 6 | 13.52
2 | Saryu Nahar Ph-III | 480 | 0 | 0 | 0 | 0 | 473 | 171.15 | 36.18
 | TOTAL | 524.381 | 0 | 0 | 0 | 0 | 663.9 | 221.15 | 33.31
(CCA in Th. ha.)
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations
* i.e. CCA developed under CADWM (up to 31-03-2019) and before CADWM inclusion.

## Slide 187
Key Reasons For Progress Delays
Status | Key Reason
√ | Absence of Hydraulic Connectivity up to Outlet.
X | Delay in Govt/Administrative clearances.
X | State budget constraints.
√ | Unwillingness of farmers.
X | Delays in tendering.
X | Capacity related issues of Implementing Agencies.
X | Capacity related issues of Contractors/Suppliers.
X | Other Issue (to be specified).
5th PIRC Meeting (Mt. Abu, 30th May 2019): Progress Review Presentations